## Gantt Chart Template
Project Timeline Template
Project Name: Timer IP
| Task Name | Start (Date) | End (Date) | Duration (Days) | %done | Column1
[5 empty] | %done | Stuck point
| Investigation | 2026-06-05 | 2026-06-08 | 3 | 100
| Design specification | 2026-06-05 | 2026-06-11 | 7 | 100
| RTL coding | 2026-06-12 | 2026-06-18 | 7 | 100
| Compilation | 2026-06-19 | 2026-06-20 | 2 | 100
| Verification Plan | 2026-06-21 | 2026-06-27 | 7 | 100
| Build env | 2026-06-21 | 2026-06-22 | 2 | 100
| 1Pass | 2026-06-23 | 2026-06-25 | 3 | 100
| All Pass | 2026-06-26 | 2026-07-02 | 7 | 100
| Coverage | 2026-07-03 | 2026-07-05 | 3 | 100
| Total |  |  | 30
Formulas:
End (Date) = [Start (Date)]+[Duration (Days)]
End (Date) = [Start (Date)]+[Duration (Days)]-1
Start (Date) = [Start (Date), row above]
Start (Date) = [End (Date), row above]+1
Note on B13: PC: Understand all function + Register bit/field: 20% + Counter: 20% + Counting mode: 20% + APB: 30% + interrupt: 10%
Note on B14: PC: Design specification making + Feature list: 10% + Block diagram: 10% + IO port list: 10% + Waveform: 30% + Logic diagram: 40%
Note on B15: PC: Calculate % based on your block diagram. For example, your module has 5 block --> each block can be 20%. Note that % for each block can be differ based on your estimation.
Note on B16: PC: Compile DUT only: 50% Write 1 simple tb, instantiate DUT and run 1 simulation (no stimulus) without Warnings/Errors: 50%
Note on B17: PC: Write verification plans to cover all features of the design. The % based on your estimation.
Note on B18: PC: Build necessary components for your env: APB master, checkers, scripts, report... ( task Apb_read and Apb_write and checker: pass,fail)
Note on B19: PC: 1PASS scenario (sanity test): a testcase that cover some basic functions of the design 1. Write 0xffff to TCMP0 and read back 2. Enable interrupt 3. Start timer 4. Check if interrupt can be asserted when timer reaches TDR0 value.
Note on B20: PC: %done is calculated based on how many items already passed in your verification plan
Note on B21: PC: Toggle: 20% Statement: 20% Expression: 20% Condition: 20% Branch: 20%